## TASKS
Planning and Schedule
MY TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Phase 1 |  |  |  | 0
Project selection and team formation | 2024-09-06 | n/a | 100% | 1
Group Meeting | 2024-09-08 | n/a | 100% | 1
Group Meeting with Professor WeiPing Zhu | 2024-09-10 | n/a | 100% | 1
Group meeting | 2024-09-11 | n/a | 100% | 1
Proposal Completed | 2024-09-15 | 2024-09-19 | 100% | 1
Project Approval by Supervisor | 2024-09-16 | n/a | 100% | 1
Phase 1 Report Submitted | 2024-09-28 | 2024-10-05 | 100% | 1
Group meeting | 2024-09-29 | n/a | 100% | 1
Meeting with Space Concordia | 2024-10-01 | n/a | 66% | 0
Group meeting | 2024-10-05 | n/a | 100% | 1
Phase 1 presentation | 2024-10-05 | 2024-10-07 | 100% | 1
0
Phase 2 |  |  |  | 0
Group Meeting | 2024-10-07 | 2024-10-07 | 100% | 1
ELSEE aspects Powerslide | 2024-10-16 | 2024-10-26 | 100% | 1
Group Meeting | 2024-10-17 | 2024-10-17 | 100% | 1
Group Meeting with Professor Christopher Trueman | 2024-10-18 | 2024-10-18 | 100% | 1
ELSEE Presentation | 2024-10-28 | 2024-10-28 | 100% | 1
Block Diagram Desgin | 2024-11-02 | 2024-11-03 | 100% | 1
Flow Chart | 2024-11-02 | 2024-11-03 | 100% | 1
Group Meeting with Professor Dmitry | 2024-11-04 | 2024-11-04 | 100% | 1
Phase 2 Report | 2024-11-10 | 2024-11-23 | 100% | 1
kicad schematic | 2024-11-05 | 2024-11-22 | 100% | 1
Group Meeting | 2024-11-22 | 2024-11-22 | 100% | 1
Group Meeting | 2024-11-23 | 2024-11-22 | 100% | 1
Phase 2 presentation | 2024-11-24 | 2024-11-25 | 100% | 1
0
Phase 3 |  |  |  | 0
Test and Prototype Video and Audio acquisition | 2024-12-01 | 2024-12-07 |  | 0
Test and Prototype IMU and heart rate sensors data acquisition | 2024-12-08 | 2024-12-14 |  | 0
Test and prototype Tracking System | 2024-12-15 | 2024-12-21 |  | 0
Test and prototype transmitting data to server | 2024-12-22 | 2024-12-28 |  | 0
Test and prototype broadcasting stream from server | 2024-12-29 | 2025-01-04 |  | 0
Test and prototype Android app | 2025-01-05 | 2025-01-11 |  | 0
Test and prototype VR goggle app | 2025-01-12 | 2025-01-18 |  | 0
Test and prototype all above functions together | 2025-01-19 | 2025-01-25 |  | 0
Design complete circuit | 2025-01-26 | 2025-01-08 |  | 0
Create PCB layout | 2025-01-26 | 2025-01-08 |  | 0
Create and validate Bill of Materials | 2025-02-09 | 2025-02-15 |  | 0
Phase 3 Demo | TBD | TBD |  | 0
0
0
Phase 4 (Final Product) |  |  |  | 0
All group meeting plan |  |  |  | 0
Final design implementation |  |  |  | 0
Verification and testing |  |  |  | 0
Phase 4 In-Lab Demo |  |  |  | 0
Phase 4 Report Submission |  |  |  | 0
Phase 4 Final Poster Presentation |  |  |  | 0
0
0
0
0
0
0
0
ALL TBD from March to April in 2025