## Sheet1
COEN 490 | [7 empty] | The 1st of every month
Sports Vision Pro | [7 empty] | Phase 1 | [11 empty] | Phase 3 expected
Group 13 | [7 empty] | Phase 2 | [11 empty] | Phase 4 expected
2024 Phase 1 & 2
Task Descrption | Starting Date | End Date | Days to complete | Progress | September | [29 empty] | October | [30 empty] | November
Phase 1 |  |  |  |  | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29
Project selection and team formation | 2024-09-06 | 2024-09-06 | 1 | 100%
Group Meeting | 2024-09-08 | 2024-09-08 | 1 | 100%
Group Meeting with Professor WeiPing Zhu | 2024-09-10 | 2024-09-10 | 1 | 66%
Group meeting | 2024-09-11 | 2024-09-11 | 1 | 100%
Proposal Completed | 2024-09-15 | 2024-09-19 | 5 | 100%
Project Approval by Supervisor | 2024-09-16 | 2024-09-16 | 1 | 100%
Phase 1 Report | 2024-09-28 | 2024-10-05 | 8 | 100%
Group meeting | 2024-09-29 | 2024-09-29 | 1 | 100%
Meeting with Space Concordia | 2024-10-01 | 2024-10-01 | 1 | 100%
Group meeting | 2024-10-05 | 2024-10-05 | 1 | 100%
Phase 1 presentation | 2024-10-05 | 2024-10-07 | 3 | 100%
Phase 2
Group Meeting | 2024-10-07 | 2024-10-07 | 1 | 100%
ELSEE aspects PowerSlide | 2024-10-16 | 2024-10-26 | 11 | 100%
Group Meeting | 2024-10-17 | 2024-10-17 | 1 | 100%
Group Meeting with Professor Christopher Trueman | 2024-10-18 | 2024-10-18 | 1 | 100%
ELSEE Presentation | 2024-10-28 | 2024-10-28 | 1 | 100%
Block Diagram Desgin | 2024-11-02 | 2024-11-03 | 2 | 100%
Flow Chart | 2024-11-02 | 2024-11-03 | 2 | 100%
Group Meeting with Professor Dmitry | 2024-11-04 | 2024-11-04 | 1 | 100%
Phase 2 Report | 2024-11-10 | 2024-11-23 | 14 | 100%
kicad schematic | 2024-11-16 | 2024-11-22 | 7 | 100%
Group Meeting | 2024-11-22 | 2024-11-22 | 1 | 100%
Group Meeting | 2024-11-23 | 2024-11-23 | 1 | 100%
Phase 2 presentation powerpoint | 2024-11-24 | 2024-11-25 | 2 | 100%
2025 Phase 3 & 4 |  |  |  |  | December | [30 empty] | January | [30 empty] | February
Task Descrption | Starting Date | End Date | Days to complete | Progress | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27
Phase 3
Test and Prototype Video and Audio acquisition | 2024-12-01 | 2024-12-07
Test and Prototype IMU and heart rate sensors data acquisition | 2024-12-08 | 2024-12-14
Test and prototype Tracking System | 2024-12-15 | 2024-12-21
Test and prototype transmitting data to server | 2024-12-22 | 2024-12-28
Test and prototype broadcasting stream from server | 2024-12-29 | 2025-01-04
Test and prototype android app | 2025-01-05 | 2025-01-11
Test and prototype VR goggle app | 2025-01-12 | 2025-01-18
Test and prototype all above functions together | 2025-01-19 | 2025-01-25
Design complete circuit | 2025-01-26 | 2025-02-08
Create PCB layout | 2025-01-26 | 2025-02-08
Create and validate Bill of Materials | 2025-02-09 | 2025-02-15
Phase 3 Demo | TBD | TBD
Phase 4
Formulas:
End Date = SUM([Starting Date],0)
TBD